## Sycle Projects Timeline
DWFRS Project List
| Project Phase | Start Date | End Date
Asset Management System | Delivery Plan | 2020-10-01 | 2022-09-01
| Bedding in | 2022-10-01 | 2023-02-01
| Evaluation | 2023-03-01 | 2023-04-01
DTP - Adoption & Migration | Delivery Plan | 2020-11-01 | 2023-09-01
| Bedding in | 2023-10-01 | 2023-12-01
| Evaluation | 2024-01-01 | 2024-02-01
Digital Transformation Programme Systems onto 365 | SMS Messaging
| Delivery Plan | 2020-11-01 | 2022-04-01
| Bedding in | 2022-05-01 | 2022-07-01
| Evaluation | 2022-08-01 | 2022-09-01
Policies and Procedures
| Delivery Plan | 2020-11-01 | 2022-03-01
| Bedding in | 2022-04-01 | 2022-06-01
| Evaluation | 2022-07-01 | 2022-08-01
Skills for Justice | Delivery Plan | 2021-10-01 | 2022-10-01
| Bedding in | 2022-11-01 | 2023-02-01
| Evaluation | 2023-03-01 | 2023-04-01
Solar Standby Power | Delivery Plan | 2021-11-01 | 2022-11-01
| Bedding in | 2022-12-01 | 2023-12-01
| Evaluation | 2024-01-01 | 2024-02-01
National Operational Guidance, Service Implementation | Delivery Plan | 2022-05-01 | 2022-06-01
Bedding in
Evaluation
Human Resource Management Information System Review | Delivery Plan | 2022-05-01
Bedding in
Evaluation
Station End Equipment | Delivery Plan | 2022-04-01 | 2022-08-01
| Bedding in | 2022-08-01 | 2022-09-01
| Evaluation | 2023-04-01 | 2023-04-01
Telephony | Delivery Plan | 2022-05-01
Bedding in
Evaluation
Support Function Review | Research and consultation | 2021-09-01 | 2022-09-01
| Decision Making | 2022-06-01 | 2023-07-01
Implementation Plan
Evaluation
Cleaner Cab | Research and consultation | 2021-10-01 | 2021-11-01
| Decision Making | 2021-11-01 | 2022-01-01
| Implementation Plan | 2022-01-01 | 2022-08-01
| Evaluation | 2022-06-01 | 2023-01-01
Technical Rescue | Research and consultation | 2019-01-01 | 2021-04-01
| Decision Making | 2021-04-01 | 2021-04-01
| Implementation Plan | 2021-04-01 | 2022-06-01
Evaluation