## Sheet1
ICT Strategy - High Level Delivery Plan v01 Nov 2021 | [5 empty] | Delivery
[6 empty] | 2021/22 | 2022/23 | 2023/24 | 2024/25
ICT Strategy: What we will do |  | Supporting Activity/Projects | Responsibility | Task Owner | Current Status
Information Governance & Security | Establish standardisation for hardware and software to provide increased assurance on compliance regardless of where developed. | ICT build standardisation documents for hardware embedded in BAU | Head of ICT | ICT Networks and Security Manager | In progress | ü
|  | ICT build standardisation documents for servers inc infrastructure mapping embedded into BAU |  | ICT Infrastructure Manager | In progress | ü
|  | Standardisation of minmum spec for hardware suppliers into DWFRS (Security/Compliance requirements) |  | ICT Infrastructure Manager | In progress | ü
|  | Standardisation of minimum spec for software suppliers into DWFRS (Security /compliance Requirements) |  | ICT Infrastructure Manager | Complete | ü
|  | Whitelist for hardware and software embedded in ICT BAU processes |  | ICT Planning & Support Manager | Complete | ü
|  | Desktop Patching |  | ICT Infrastructure Manager | Ongoing BAU | Ongoing as part of BAU
|  | Asset management System Replacement Project (see project details below) |  | ICT Planning & Support Manager | In progress
| Support and develop fit-for-purpose software systems (in house and externally purchased) that meet the needs of the Service. | Digital transformation programme (See project details below) | Head of Corporate Support | Multi teams | In progress
|  | Software & Upgrade reviews with business owners | Head of ICT | ICT Planning & Support Manager | Ongoing BAU | Ongoing as part of BAU
|  | Quarterley meetings with business owners to review business needs and upcoming new projects | Head of ICT | Head of ICT | Ongoing BAU | Ongoing as part of BAU
|  | ICT business requirements engagement in Business Case development processes across service as part of Strategic Planning business case submission process | ALL DEPARTMENTS | Head of ICT | Ongoing BAU | Ongoing as part of BAU
| Centrally manage all end user hardware devices online to assure security updates and patching is applied consistently reducing the risks to the service infrastructure. | Intune Project - all hardware managed through Intune as part of BAU processes | Head of ICT | ICT Networks and Security Manager | In progress | ü
|  | End User Automatic Device patching (linked to asset manager - will identify, but need a tool for automatic updates) | Head of ICT | ICT Networks and Security Manager | Not started |  | ü
|  | Server Room Security Reviews and Upgrades | Head of ICT | ICT Networks and Security Manager | Ongoing BAU | Ongoing as part of BAU
|  | Asset Management System Replacement Project | Head of ICT | ICT Planning & Support Manager | In progress | ü | ü
| Review our Mobile Device Management and Log Monitoring systems to ensure we make best use of resources and the new technologies available. | MDM part of InTune Project (see above ) | Area Manager Service Support | ICT Networks and Security Manager | In progress
|  | Log Monitoring Systems Review | Head of Corporate Support | Cyber Security Manager | Not started | ü | ü
| Assure our firewalls are continually fit-for-purpose, meeting the ESN code of connection requirements, as well as being sustainable to support online partnership working. | ESN CoCo Submission & Subsequent Sign Off by Auditors | Director of Service Support | ESMCP Project manager | Ongoing BAU | Ongoing as part of BAU
|  | ICT Annual Health Check and Action Plan Delivery | Head of ICT / Head of Corporate Support | Multi teams | Ongoing BAU | Ongoing as part of BAU
| Simplify password management whilst still maintaining security compliance requirements | See project below - linked with Windows 11 rollout | Head of ICT | ICT Infrastructure Manager | In progress
| Continue to raise awareness and train our staff in information security. | Awareness Training | Head of Corporate Support | Cyber Security Manager | Ongoing BAU | Ongoing as part of BAU
|  | Cyber Action Plan | Head of Corporate Support | Information Governance Manager & Data Protection Officer |  | Ongoing as part of BAU
| Replace end point protection | Bit Defender | Head of ICT | ICT Networks and Security Manager |  | ü
| Implement Office 365 mail protection. | Review | Head of ICT | ICT Infrastucture Manager |  |  | ü
Operational Comms | Develop use of MDT (Mobile Data Terminals) technology, replacing the current hardware with more flexible devices. | MDT Review | Area Manager Service Support | Operational Communications Manager | In progress | ü | ü
| In line with the Emergency Services Mobile Communication Programme, transition from Airwave to ESN for all critical operational communications. | ESN project | Area Manager Service Support | Operational Communications Manager | In progress |  | ü | ü | ü
| Develop and implement new technology for risk management as part of a wider Fire Risk Management project. | CFMIS Project | Area Manager Prevention & Protection | Multi teams | In progress | ü | ü
| Work closely with fleet and equipment to ensure future technical capabilities form part of specification, procurement and delivery of new appliances | New Appliance Project | Area Manager Service Support / Head of Assets / Head of ICT | Fleet & Equipment Project Manager | In progress | ü
|  | Special Vehicle Replacement Project |  | Special Vehicles Programme Manager | In progress |  | ü
| Offer improvements for flexi duty officer's ways of working through integrated devices and software. | ESN Project | Director of Service Support | ESMCP Project manager | In progress | ü | ü
|  | New hardware device trials | Director of Service Support | ESMCP Project manager | In progress | ü | ü
|  | Increased use of Bodyworn Cameras | Area Manager Learning & Organisatinal Development | SM Training & Command Projects Manager | In progress |  | ü
| Support delivery of new command and control system. | Command and Control Review | Area Manager Service Support | Operational Communications Manager | TBC |  | ü | ü
| Identify opportunities to deliver value for money while matching organisational needs. | NFSP | Area Manager Service Support | NFSP Partnership Manager | Ongoing BAU | Ongoing as part of BAU
ICT Resiliance | Update the distributed Server Farm and investigate benefits of hybrid and/or cloud delivery of the server farm for future proofing. | Server SAN replacement | Head of ICT | ICT Infrastructure Manager and ICT Networks & Security Manager | In progress | ü | ü
| Ensure the OS (Microsoft Data Centre 2012) is fit-for purpose, review these products at the same time the servers are replaced/upgraded for sustainability. |  |  | ICT Infrastructure Manager | In progress | ü | ü
| Distributed data storage system (linked to distributed server farm activity above) to be reviewed and replaced where appropriate including reviewing the on-going storage requirements to ensure that the current Service needs and new ways of working are met. |  |  | ICT Infrastructure Manager and ICT Networks & Security Manager | In progress | ü | ü
| Review Mutiny firewall software alongside other monitoring systems in place to against business requirements to ensure right tools are in place, vulnerability gaps are closed no overlaps and or duplication across systems to assure value for money. | Review of all monitoring tools and gap analysis of business requirements to inform new solutions and processes | Head of ICT / Head of Corporate Support | Cyber Security Manager | Not started |  | ü
|  | Cyber Action Plan / ICT Health Check / CoCo Submission |  | Multi teams | Ongoing BAU | Ongoing as part of BAU
|  | Review of Roles and Responsibilities across ICT Network & Security Manager and Cyber Security Manager to provide assurance and ownership |  | Information Governance Manager & Data Protection Officer | Ongoing BAU | ü
Technology Management | Review the replacement programme annually in line with the smarter ways of working agenda to ensure that users have the right hardware to meet the needs of the service and their role. | Hardware procurement & replacement (rolling programme throughout year) | Head of ICT | ICT Planning & Support Manager | Ongoing BAU | Ongoing as part of BAU
| Review the new telephony needs across the service and deliver a new solution to improve efficiency, reliance and reduce costs. | Telephony Project |  | ICT Infrastructure Manager | In progress | ü | ü | ü
| Station Uninterruptible Power Supply (UPS) replacements will be undertaken based upon age and battery life predictions. Full replacement expected in 2025 with a move to a consistent make and model across all stations to ensure ease of maintenance. | UPS replacement review | Area Manager Service Support / Head of Assets | Operational Communications Manager |  |  |  | ü | ü
| Replacement of Multitone station end equipment replacing the operating system to maintain security. | Multitone Review | Area Manager Service Support | Operational Communications Manager |  |  | ü
| More efficient processes and technology to manage business requirements of hardware. | ESN Project | ALL OPERATIONAL DEPARTMENTS | ESMCP Project Manager | In progress | ü | ü | ü | ü
|  | Mobile phone replacement programme | Head of ICT / Area Manager Service Support | Operational Communications Manager | Ongoing BAU | ü | ü | ü | ü
|  | Operational fire fighter technology review of needs | Area Manager Response | u/k | Not started |  | ü
|  | Laptop replacement programme (see above in line 40) | Head of ICT | ICT Planning & Support Manager | Ongoing BAU | ü | ü | ü | ü
| Support the Service in identifying how technology can support delivery of training and align this vision to capital and project development programmes | Operational fire fighter technology review of needs | Area Manager Response | u/k | Ongoing BAU | Ongoing as part of BAU
|  | Quarterly project reviews with Training Department | Head of ICT | Head of Training | Ongoing BAU | Ongoing as part of BAU
Digital Transformation | Document migration programme from file shares to SharePoint. | Digital Transformation Programme Workstream - Document Migration | Head of Corporate Support | Multi teams | In progress | ü | ü
| Reduce reliance on historical systems making best use of current investments | Digital Transformation Programme Workstream - Notes systems into Office 365 | Head of ICT | ICT Projects & Buisness Relationships Manager | In progress | ü | ü
| Develop fit for purpose systems and processes to meet the current business needs, providing sustainability and reducing future risks | HR processes and systems review project - in line with digital transformation and business requirements | Director of People Services | Head of HR | In progress | ü | ü
| Process improvements using tools in office 365 | Aligned to above data migration and NOTES into o365 - develop more efficient processes to assure efficiencies in ways of working | ALL DEPARTMENTS |  | In progress | ü | ü
| Adopt a Cloud first approach wherever possible when procuring new systems and software to reduce infrastructure costs. | Ongoing task throughout all ICT strategy development | ALL DEPARTMENTS |  | Ongoing BAU | ü | ü
| Maintain and develop specialist skills in line with technological changes. | Ongoing ICT & Digital Transformation team development programme | Head of ICT / Head of Corporate Support | Information & Procees Improvement Officer | Ongoing BAU | Ongoing as part of BAU
|  | Ongoing resource planning, skills upgrade across all operational and corporate teams in line with HR workforce planning processes and training departments |  | ALL Departments Leads | Ongoing BAU | Ongoing as part of BAU
|  | Phoenix Consultancy Support Project |  | ICT Projects & Business Relationships Manager | In progress | ü | ü
| Provide training and support to end users to facilitate the cultural changes associated with embracing new technology and smarter ways of working. | Training programme aligned to digital transformation programme workstreams | Head of Corporate Support | Information & Procees Improvement Officer | Ongoing BAU | Ongoing as part of BAU
| Review bandwidth against business needs and increased remote access requirements, as well as accounting for change to web based and cloud ways of working | Review bandwidth on a annual basis in line with ICT and wider service business needs, ensure environmental scanning for any dependent impacts or risks | Head of ICT | ICT Infrastructure Manager | Ongoing BAU | ü | ü
| Improve authentication and implement single sign-on to as many applications as possible to improve efficiency and security. | SSO Project | Head of ICT | ICT Infrastructure Manager | Not started |  | ü
Business Intelligence and Data Management | Continued use of PowerBi and Office 365 tools to integrate data and provide client focused useable front end. | Digital Transformation Programme | Head of Corporate Support | Information Systems Manager Corp Support | Ongoing BAU | Ongoing as part of BAU
| Migration of corporate systems to hosted environments. | Digital Transformation Programme | Head of ICT / Head of Corporate Support | ICT Infrastructure Manager | In progress | ü | ü
| Establish clear data retention processes for all corporate systems. | Part of governance for Digital Transformation Programme above Wider work ongoing with IAO and IAAs across service | Head of Corporate Support | Information Governance Manager & Data Protection Officer | In progress | ü
| Review approach to mapping in terms of Service benefits and NFSP collaborative working | NFSP | Area Manager Service Support | TBC | In progress | Ongoing as part of BAU