## Sheet1
Project | Report Title | Recommendation description | Due date | Service Update Summary | Is this recommendation complete?
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | With immediate effect, chief fire officers should review their implementation of the Core Code of Ethics and make sure it is being applied across their services. | 2023-03-30 | The code of ethics was implemented in the Service on 1st January 2022. Its introduction followed the creation of a Code of Ethics handbook and various articles and staff communications. All relevant procedures have been aligned to and reference the code of ethics and the Code of Ethics signage is displayed across our workplaces. The HMICFRS inspection report commented that almost all respondents to the HMICFRS staff survey (233 out of 234) were aware of service values. This demonstrates that the code of ethics is embedded in the workplace. Similarly, staff understanding of the code of ethics was positively acknowledged within the staff survey undertaken as part of the internal culture review arising out of the LFB culture report. This survey identified strong application of this service wide, across all staff groups. We have recently completely a Quality Assurance audit of our implementation of the code of ethics, as part of our QA of Fire Standards implementation An evaluation of the code of ethics is included in our Service Delivery plans but we have been awaiting communication from the NFCC. Our new 360 tool is aligned to the code of ethics. A temperature check on the degree to which staff feel the Service works in alignment with the code of ethics will form part of the staff survey. We are also developing an E Learning course to ensure that whilst the Code of Ethics has embedded, focus on its importance is maintained. We have looked at good practice in other Services to identify ways our approach can be further strengthened | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 August 2023, chief fire officers should develop plans to promote progression paths for existing staff in non-operational roles and put plans in place to reduce any inequalities of opportunity. | 2023-08-01 | All staff have a 1:1 review with their line manager at which they have a structured conversation about their wellbeing, performance, and development. Action plans can be developed from these discussions. All staff have access to development pathways and other leadership development tools via our Learning Hub. The Hub holds numerous development materials that can be accessed to support professional and personal development. Leadership Development programmes are in place at supervisory and middle manager level. Course attendance is drawn from all parts of the Service and all staff groups so that there is greater diversity of thinking to enhance cultural cohesion. Staff at Station Manager and corporate equivalent and above attend Leaders Forums where leadership topics are discussed. All staff at this level have completed colourwork profiles to aid self-awareness and personal development. All staff have access to mentoring and coaching opportunities and ‘open seats’ are available for staff to attend key meetings. We also encourage and support all staff to undertake apprenticeships and a variety of apprenticeships are currently underway in topics such as business administration, project management, finance, chartered manager. Our approach is continually reviewed to ensure good practice and alignment to NFCC products. It is likely that our Independent Review will include improvements that will need to be addressed through our leadership and learning and development activities. All these opportunities are promoted in our weekly update and Firewire articles and also at manager briefing sessions. Views of our staff networks are sought in order to enhance our offerings or supporting ideas that come forward. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should, as a priority, specify in succession plans how they intend to improve diversity across all levels of the service. This should include offering increased direct-entry opportunities. | 2023-06-01 | Our People and EDI strategies both include plans to strengthen the diversity of our workforce, and this is a priority for the Service. A strategic workforce plan is also in place and aligns to the Strategic Assessment of Risk and our Community Safety Plan. Our workforce planning arrangements were deemed as Outstanding by HMICFRS in 2022/23. Department succession plans are in place for every Directorate/Department. Heads of Department, working closely with their HRBP, review the plans on an annual basis, with a progress check at six months. The succession plans include tools such as the nine-box grid, FRS succession and talent management and a leavers risk matrix. These tools enable the service to identify talent and aid 1:1 review discussions. When vacancies occur discussion takes place regards whether it is a ‘like for like’ replacement or whether there are any opportunities for change which would support talent management. This was done at Strategic level, when the uniformed ACFO role was advertised as a uniformed ACFO or a corporate ACO role depending on the successful applicant. As the role become a corporate role a DACFO (Deputy Assistant Chief Fire Officer) post was created which gave succession planning and development opportunities for Area Managers to work and gain experience on the Brigade Manager rota. Leadership Development programmes and development pathways are in place, along with a wide range of personal and professional development resources including coaching and mentoring . As part of our commitment to diversity, six operational females are currently undertaking the ‘Our Time’ progression scheme. We are committed to the talent management of our staff and have a range of measures to break down barriers and increase diversity across our workforce, this includes a corporate target to improve the diversity of our workforce as a whole. The strategic workforce plan has a planned review imminently to cover the period 2023 – 2025 to ensure continued alignment with the Strategic Assessment of Risk. A focus of this plan will include actions to increase the diversity of our workforce. The Service has not been able to take part in the national Direct Entry scheme as there is a need for the individual to be ‘supernumerary’. Our establishment is tightly controlled and is not able to have such additional budgetary commitments at this currently time due to organisational restructures and downsizing department/teams/station crewing. We will monitor the progress of other Services who have opted for direct entry for future consideration should our budgets and succession plans allow. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should review how they gather and use equality and diversity data to improve their understanding of their staff demographics, including applying and meeting the requirements of the National Fire Chiefs Council equality, diversity and inclusion data toolkit [https://www.ukfrs.com/equality-diversity-and-inclusion-data-toolkit]. | 2023-06-01 | We collate a wide range of equality data for our staff, paying due regard to the NFCC EDI data toolkit. We publish our Annual Workforce Equality Data report alongside our annual report. This includes detailed analysis of our staff against some of the protected characteristics providing an overview and context alongside our future aspirations. Approximately 2 years ago, we undertook our 'safe to say' campaign which resulted in our staff being better educated regards the importance of the Service maintaining up to date equality data. The annual equality data includes benchmarking against other FRSs. As part of our digital transformation programme we have a project to replace our HR management information system (HRMIS) A key benefit of a new system will be the ability to generate real time data, in particular equality data. This data is already collated but the intention is that the new system will assist in a more streamlined, accessible data reporting functionality. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 October 2023, as a precursor to the development of the College of Fire and Rescue, chief fire officers and the National Fire Chiefs Council should work with the Home Office to consider how they can improve the training and support they offer to staff in management and leadership development. This should include authority members in respect of their assurance leadership roles and should ensure that opportunities are offered fairly across all staff groups. | 2023-10-01 | Not withstanding information coming forward from the NFCC we are reviewing our leadership development programme. This review will also capture any recommendations from our independent review once published. We have revised our leadership development programme to strengthen behavioural aspects of leadership development and in the process of rolling this out. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 October 2023, chief fire officers should put plans in place to monitor, including through the gathering and analysis of staff feedback, watch and team cultures and provide prompt remedial action for any issues they identify. | 2023-10-01 | following the publication of the LFB report, in Dec 22 we set in place an internal cultural review. In March 23 we commissioned an independent cultural review. Over 250 staff (and ex employees) took part in this review. We are awaiting the report from this review and intend to create one single action plan drawn from the recommendations of our internal culture review , our independent review as well as any actions arising out of the spotlight report and the NFCC culture action plan. Oversight of the delivery of the action plan will be through our culture development committee and will be reported to the Fire Authorities Finance and Audit Committee on a quarterly basis. As part of our communication and engagement plan, we will undertaking regular staff surveys to ensure our staff are psychologically safe, well supported and confident to raise any concerns. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should seek regular feedback from staff about values, culture, fairness and diversity, with due regard to the leading and developing people standard [https://www.firestandards.org/standards/approved/leading-developing-people-fsc-led01a/]. They should show how they act on this feedback. | 2023-06-01 | There are a range of mechanisms in place for staff to provide feedback. This includes pulse surveys, Bitesize Leaders Forum, Manager Engagement Days, Group/On-Call Question Time sessions. The Service has completed an internal cultural review and commissioned an independent cultural review. Feedback and observations from these processes has been reviewed and generated a cultural action plan which is communicated across the Service and remains an ongoing evaluation and assessment. We are planning to reintroduce staff surveys and ensure these ‘climate’ surveys have a particular focus on values, culture, fairness, and diversity. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 September 2023, chief fire officers should make sure there is a full, 360-degree feedback process in place for all other leaders and managers in service. The process should include gathering feedback from a wide range of sources including colleagues and direct reports. | 2023-09-01 | All senior leaders have undertaken a 360 assessment and our revised leadership development programme will incorporate the 360 assessment process. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should make sure there is a full, 360-degree feedback process in place for all senior leaders and managers (assistant chief fire officer equivalent and above) in service. | 2023-06-01 | SLT Development days have included ‘facilitated’ discussions so that team members are able to provide open and honest feedback to each other in a safe environment. Feedback was also sought from the managerial grades below, with actions recorded to ensure implementation. SLT have also looked at how they come across at corporate meetings and have received 1 to 1 feedback and coaching on their individual style by an external facilitator. SLT use the Insights ‘Colourworks’ profiles which enables individuals to be aware of their ‘blind spots’ and how they may be perceived by others so that individuals are aware, and changes set in place. We have worked with our Colourworks provider to develop a bespoke 360 tool that is aligned to the Code of Ethics. This will be launched to SLT on 26th June so that it can be used as part of SLTs Development Day on 20th July 2023. | Yes, 360 launches on 26 June 2023
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should have plans in place to ensure they meet the Fire Standards Boards leading the service standard"[https://www.firestandards.org/standards/approved/leading-the-service-fsc-led01b/] and its "leading and developing people standard" [https://www.firestandards.org/standards/approved/leading-developing-people-fsc-led01a/]. | 2023-06-01 | The gap analysis using the NFCC tool has been completed and an action plan developed. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 August 2023, chief fire officers should provide assurances to HMICFRS that all parties are supported in relation to ongoing investigations. | 2023-08-01 | A range of support mechanisms are in place to ensure all parties are supported. These are available through on our internal CONNECT site and detailed within our Health and Wellbeing procedure. Our counselling service is well publicised and enables individuals to self-refer. Those involved in investigation processes are advised of wellbeing arrangements available to them in written correspondence. For individuals under investigation, a contact officer is always appointed. HR Business Partners are assigned to all stations and departments so that they can provide dedicated support to staff. Support can also be provided by an individual’s trade union or staff network group and when appropriate contact can be made with the relevant trade union to ensure lines of communication are clear. A workplace concerns poster is displayed in every workplace which provides QR codes to associated procedures and signposts points of contact. We are looking at to enhance mental health support arrangements and a culture dashboard is being developed, which will be launched in September. The dashboard will provide transparent performance information to raise staff awareness and confidence. As part of our approach to increase confidence in raising concerns a one-stop support portal will be launched in September enabling staff to easily raise concerns without the need to read through procedures. In September we will be introducing a confidential external reporting line as part of the FRS Speak Out campaign. We are also looking at introducing ‘Speak Up Guardians’ are learning from other sectors/Services who have introduced this. The terms of reference of our independent review will also provide recommendations with regard to how we can further support staff. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | With immediate effect, chief fire officers should notify HMICFRS of any allegations that have the potential to constitute staff gross misconduct that: - involve allegations of a criminal nature that have the potential to affect public confidence in FRSs; - are of a serious nature; or - relate to assistant chief fire officers or those at equivalent or higher grades. | 2023-03-30 | When this situation occurred the HMICFRS’s Service Liaison Lead was notified. Data providing this information has been uploaded. | Yes, and will be ongoing
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 March 2024, chief fire officers should provide assurances to HMICFRS that they have implemented the standard on misconduct allegations and outcomes handling. | 2024-03-01 | We have reviewed the published changes that have been made to the standards and have re-completed a GAP analysis and assessed that we remain fully compliant with these | Complete
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 March 2024, chief fire officers should provide assurances to HMICFRS that they have implemented the standard on staff disclosure, complaint and grievance handling. | 2024-03-01 | We have reviewed the published changes that have been made to the standards and have re-completed a GAP analysis. We have a process in place to undertake DBS checks for all new starters. We have recently appointed a 3rd party provider to undertake all necessary checks for current staff and anticipate that this work will be completed by the end of June 2024. The ACO, Director of People Services continues to have weekly meetings with the AM Prevention/Protection to review and risk assess any information arising as a result of completed DBS checks. | Complete
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 January 2024, chief fire officers should: - immediately review their current background checks arrangements, and make sure that suitable and sufficient background checks are in place to safeguard their staff and communities they serve; and - make sure that appropriate DBS check requests have been submitted for all existing, new staff, and volunteers, according to their roles as identified by the Fire Standards Board. | 2024-01-01 | A pre-employment check procedure is in place sets out our approach to this. Following the change to legislation in July 2023 we commenced employment checks of all new staff at standard level (except in roles that required enhanced). We are using the NFCC safeguarding tools and guidance, in particular the risk assessment process, should any issues arise. A panel (HR and Safeguarding) meets on a weekly basis to review any risk assessments completed and to consider an agreed way forward. Decisions are recorded and stored confidentially. Our website and all recruitment adverts indicate the level of DBS check required for each role. The Service conducts Enhanced DBS checks on those individuals in posts who carry out any ‘regulated’ activity with vulnerable groups, as defined by the Safeguarding Vulnerable Groups Act 2006, for example, Safeguarding Lead, and members of staff who work regularly with children such as Firesetters Advisors. DWFRS did not undertake any rechecks of staff (excepting those signed up to the update portal). A paper regarding rechecking of existing staff was considered by the Strategic Leadership Team (SLT) in dec 23 and this will be set in place in march 24, following completion of our procurement process. Our process is currently administered by an external service provider (currently Dorset Council) but due to the increase in checks required we have exceeded procurement thresholds and must complete a three quote procurement process (for the checking of current staff element). Our procedure has been updated to reflect our revised approach with new starters and will shortly be further updated to set out our approach to checking existing staff. We have communicated this change to staff and representative bodies through our organisational communications and have taken legal advice which has advised that as we are changing terms and conditions, staff need to be written to and contracts of employment updated. Whilst we are amending these areas we are planning a structured roll out of staff rechecks and will be using the NFCC risk assessment should issues arise. This 'new work' will be picked up by a new HR resource who started in January 2024. We will be creating an MS form for all staff to complete annually which will enable us to recheck staff via the DBS service every 5 years. As our West Moors Training Centre is based on a Ministry of Defence (MOD) site at West Moors, anyone working permanently from the Training Centre is required to be Security Checked (to SC level) via the MoD. In addition, regular persons based onsite at WMTC must have SC clearance which is administered by MOD/WMTC. Therefore, non-Enhanced DBS roles at WMTC only need a Basic DBS check. We also have full Security Checked (to SC level) by the Home Office for several of our officers and corporate staff depending on role undertaken. This includes Station Manager NILOs, all Group Managers and above, as well as other members of staff who are working within or supporting the Service Resilience Teams. This is centrally overseen. | complete
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should make sure they provide accessible information for all staff and members of the public on how they can raise concerns and access confidential support (including through external agencies). Chief fire officers should also make sure accessible information is provided on how concerns and allegations will be investigated in a way that ensures confidentiality and is independent of the alleged perpetrator. | 2023-06-01 | Individuals who raise such concerns are provided with the contact details for our confidential counselling support. Counselling support can be accessed through a self-referral basis and information regards this is available on our CONNECT information site. HR Business Partners are also available to provide support, guidance and advice. A workforce concerns poster is displayed at all workplaces, and includes a QR code for staff to be able to easily access the relevant procedures and support. The poster also signposts other sources of support and advice including representative bodies and staff networks. Our whistleblowing procedure is published on our website, staff intranet and in all workplaces. This includes the ability to go through external parties such as Internal Auditors and the Authority’s Clerk and Monitoring Officer. Complex cases or cases of serious concern are investigated using external parties, who have the necessary skills and qualifications to independently carry out investigations. | Yes, but will be reviewed following the outcome of our Independent Review
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should assure themselves that updates on how concerns are being handled are shared with those who have raised them. The updates should be given in an accessible way that encourages trust and confidence in the service response. Consideration should be given to creating a professional standards function to handle conduct concerns in service (or from an external service) to have oversight of cases, to make sure they are conducted in a fair and transparent way and to act as a point of contact for all staff involved. | 2023-06-01 | The Service’s GDPR procedure and guidance provides for some levels of information to be shared where appropriate. We already publish anonymised outcomes on our staff intranet CONNECT and the Head of HR occasionally attends network meetings to provide further information and to build staff confidence. Currently individuals who have raised concerns are provided with generic advice iso as not to breach confidentiality. In this regard where actions has resulted from an issue/concern, those raising concerns are advised ‘appropriate management action has been taken’. The Independent Review Terms of Reference states “Validate the extent to which the Service currently communicates the outcomes of disciplinary procedures and make recommendations to promote increased transparency whilst maintaining compliance with employment law and legal requirements overseen by the Information Commissioners Office.” | Yes, although we will need to consider the recommendations set out in our Independent Review in relation to this to consider whether we need change the level of details in the communication of outcomes to those who have raised allegations.
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should review the support available for those who have raised concerns and take any action needed to make sure these provisions are suitable. | 2023-06-01 | Individuals who raise such concerns are provided with the contact details for our confidential counselling support. Counselling support can be accessed through a self-referral basis. Our counselling service provide statistics with regards to number of staff accessing the counselling support. This is likely to be an outcome of the Independent Review. The support available to staff involved in Discipline and Grievances has already been strengthened and better linked to our counselling service. HRBPs are also ‘on the ground’ support to staff. We have an evaluation process where we seek feedback from everyone involved in a case regarding the support they receive throughout the process. A business case setting out a range of options to enhance our mental health support provision is being developed for consideration by the Resources and Savings Programme in July 2023. | Yes, although we will need to consider the recommendations set out in our Independent Review in relation to this to consider whether we need change the level of details in the communication of outcomes to those who have raised allegations.
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 October 2023, chief fire officers should make sure their services provide a confidential way for staff to raise concerns and that staff are aware of whistleblowing processes. | 2023-10-01 | The Service has a well embedded confidential reporting process. There is guidance held on the policies and Procedures intranet site as well as on the Corporate Assurance CONNECT page. This is supported by an available e-learning package. Corporate assurance ensure that the procedure and elearning is signposted twice a year to ensure that all service personnel are aware of this and confidential reporting is also highlighted on our raising concerns posters which are distributed across our estate . Additionally, the confidential reporting procedure is one of the mandatory documents that all new starters to the Service should read as part of the induction process. We offer routes both internally and externally to report concerns. This approach will be enhanced going forward as we will be offering the Crimestoppers confidential reporting line as part of our arrangements. | Yes
Dorset and Wiltshire FRS | Values and culture in fire and rescue services | By 1 June 2023, chief fire officers should make sure their equality impact assessments are fit for purpose and, as a minimum, meet the requirements of the National Fire Chiefs Council equality impact assessment | 2023-06-01 | The Service has a robust and embedded process in place to complete Equality Impact Assessments (EIA). This is a two-stage process, based on the NFCC tool kit. Completion of EIAs is closely monitored and procedures cannot be published until the relevant stage EIA has been completed and approved. Equality Impact assessments were independently reviewed by the HMICFRS in the Service inspection that took place in 2022. Their assessment of our arrangements was: “The service has an effective process in place to assess the equalities impact on existing and new processes. The equality impact assessments we reviewed were completed to a good standard and both internal and external equality groups were consulted” | Yes